## June - 2026
Task Priority
2026-07-18 | Tasks
| Completed |  | 110
| In-Progress |  | 1
2026-01-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | connected with my team explained LMS backed the and connected with kuberan to integrate lms | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 13:00 | High | 1:30 | working on the lms admin potal backend | Completed
|  |  |  | 14:00 | 18:30 | Low | 4:30 | working on the lms admin potal api integration with kuberan | Completed
0:00
2026-02-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign and checking up the projects | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 13:00 | High | 1:30 | lms api integration with kuberan and developing new api accoding to kuberan's request | Completed
|  |  |  | 14:00 | 18:00 | Medium | 4:00 | revivew the works and connect the api integration and review errors | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet | Completed
0:00
2026-03-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 13:00 | High | 1:30 | lms api integration and help kuberan integrate backend and frontend | Completed
|  |  |  | 14:00 | 18:30 | Medium | 4:30 | lms new api creation such as assignment and test | Completed
0:00
2026-04-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign and intro to follei with the team | Completed
|  |  |  | 11:30 | 18:00 | High | 6:30 | lms api integration and new DB Schema integration | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet | Completed
0:00
2026-05-06 | 10:00 | 19:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | integrating the api on lms | Completed
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | review thw works and integrating the apis | Completed
|  |  |  | 18:00 | 19:00 |  | 1:00 | meet and countinue the lms work | Completed
0:00
2026-06-06 | 10:00 | 18:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task | Completed
|  |  |  | 11:00 | 14:00 | High | 3:00 | working on the lms api integration | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | working on the lms api integration | Completed
0:00
2026-07-06 | [6 empty] | 0:00 | SUNDAY
0:00
2026-08-06 | 10:00 | 19:45 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | working on lms api integration and assist with kuberan | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | review the works and explain about flow of new onboarding flow for folleu to interns | Completed
|  |  |  | 18:00 | 19:45 | Medium | 1:45 | lms integration | Completed
0:00
2026-09-06 | 10:00 | 24:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | lms api integration | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | lms api integration and review the works | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet | Completed
|  |  |  | 18:30 | 24:00 | High | 5:30 | lms api integration | Completed
0:00
2026-10-06 | 0:00 | 13:00 | lms | 0:00 | 6:00 | High | 6:00 | lms api integration | Completed
|  |  |  | 8:00 | 13:00 | Medium | 5:00 | lms api integration and planning for follei RAG systems and assign the task to everyone | Completed
0:00
0:00
2026-11-06 | 10:00 | 19:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task | Completed
|  |  |  | 11:00 | 14:00 | High | 3:00 | lms api integration | Completed
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | connect with syed and plan MCPs | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet | Completed
|  |  |  | 18:30 | 19:30 | Medium | 1:00 | review the backend and host it | Completed
0:00
2026-12-06 | 10:00 | 19:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task | Completed
|  |  |  | 11:00 | 14:00 | High | 3:00 | lms api integration | Completed
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | lms api integration | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet | Completed
|  |  |  | 18:30 | 19:30 | Medium | 1:00 | review the works and lms api integration | Completed
0:00
13/06/2026 | 10:00 | 18:00 | lms | 10:00 | 14:00 | High | 4:00 | checking the lms api data missing and error and then not connected api list
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | connecting the pending api and take list for student pending api data list | Completed
[7 empty] | 0:00 |  | Completed
14/06/2026 | [6 empty] | 0:00 | SUNDAY
0:00
15/06/2026 | 10:00 | 19:30 | task assign and lms | 10:00 | 14:00 | Medium | 4:00 | task assign connecting the pending api and take list for instructor pending api data list | Completed
|  |  |  | 15:00 | 19:30 | High | 4:30 | connecting the pending api and take list for admin pending api data list | Completed
0:00
16/06/2026 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign and explain the follei flow | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | creating the new folder structure for follei and link to git hub and create new RAG chnages on follei | Completed
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | Fixing The Rag for the follei and asigned backend to interns | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet | Completed
0:00
17/06/2026 | 10:00 | 0:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and task assign to ervery one | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | Review the backend code and merging | Completed
|  |  |  | 15:00 | 16:00 | Medium | 1:00 | fixing the some issues on lms and backend api url change | Completed
|  |  |  | 16:00 | 20:00 | Low | 4:00 | basic miagrations and docker containers creation | Completed
|  |  |  | 21:30 | 0:00 | High | 2:30 | working on leads api | Completed
0:00
18/06/2026(17&18 night shift) | 0:00 | 5:00 |  | 0:00 | 5:00 | Medium | 5:00 | working in miagrating FOLLEI to the office pc and merge te backend and frontend and create docker containers | Completed
0:00
18/06/2026 | [6 empty] | 0:00 | COMPENSATION FOR PREVIOUS DAY NIGHT SHIFT
19/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | task assign | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | merging the files and checking the correction on yesteday task pages | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | implementing MCPS
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | working on LMS updates | Completed
Completed
Completed
20/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | review interns code with naveen | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | review session with interns and a meet with naveen sir | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | implementing syed's MCPs AND WORKING ON THEM | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | working on LMS updates | Completed
22/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | review interns code with rajdeep and meet | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet | Completed
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | implementing new api and created new two users in LMS coireiand super admin | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | rviewing the backend code and fincing issues assiged to syed and vijayalaksmi | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | cms work started | Completed
23/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | work on lms remaining API and fixed a DB error | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | implementating cms in lms | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | Fixing follei | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed
24/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | work on lms new api and review | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | implementating cms in lms | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | follei models | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed
25/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | LMS Error debugging | Completed
26/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | work on lms new api and review | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | implementating in new apis in folllei | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | follei integration | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed
26/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | crm integration | In-Progress
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | implementating in new apis in follei, rag working | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | follei integration | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed
27/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | folei code miagration and merging started | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | crm in follei | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | follei integration | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed
28/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | LMS miagration and merging started | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | lms database issue resolved | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | LMS DB UPDATING | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes and tasks | Completed
29/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | follei new updates and calls porviding research | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | mails and sms finished | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | whsatsapp working | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed
30/06/2026 | 10:00 | 18:30 | task assign | 10:30 | 11:00 | Medium | 0:30 | LMS Integration with frontend and plan based security added | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet
|  |  |  | 12:00 | 14:00 | Medium | 2:00 | lms mails fuinction created | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | lms login mail updates added | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet
|  |  |  | 18:30 | 19:00 | Medium | 0:30 | rviewing codes | Completed

## July - 2026
Task Priority
2026-07-18 | Tasks
| Completed |  | 47
| In-Progress |  | 0
Date | Check - In Time | Check - Out Time | Task | Task Start Time | Task End Time | Task Priority | Hours | Notes | Task Progress | Blocker's (if so, How many and what are they) | Status
2026-01-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | connected with my team explained LMS backed the and connected with kuberan to integrate lms |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 13:00 | High | 1:30 | working on the lms admin potal backend |  |  | Completed
|  |  |  | 14:00 | 18:30 | Low | 4:30 | working on the lms admin potal api integration with kuberan |  |  | Completed
0:00
2026-02-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign and checking up the projects |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 13:00 | High | 1:30 | lms api integration with kuberan and developing new api accoding to kuberan's request |  |  | Completed
|  |  |  | 14:00 | 18:00 | Medium | 4:00 | revivew the works and connect the api integration and review errors |  |  | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet |  |  | Completed
0:00
2026-03-06 | 10:00 | 18:30 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 13:00 | High | 1:30 | lms api integration and help kuberan integrate backend and frontend |  |  | Completed
|  |  |  | 14:00 | 18:30 | Medium | 4:30 | lms new api creation such as assignment and test |  |  | Completed
0:00
2026-07-04 | [6 empty] | 0:00 | SUNDAY
0:00
2026-05-06 | 10:00 | 19:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | integrating the api on lms |  |  | Completed
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | review thw works and integrating the apis |  |  | Completed
|  |  |  | 18:00 | 19:00 |  | 1:00 | meet and countinue the lms work |  |  | Completed
0:00
2026-06-06 | 10:00 | 18:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task |  |  | Completed
|  |  |  | 11:00 | 14:00 | High | 3:00 | working on the lms api integration |  |  | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | working on the lms api integration |  |  | Completed
0:00
2026-05-06 | 10:00 | 19:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | task assign |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | integrating the api on lms |  |  | Completed
|  |  |  | 15:00 | 18:00 | Medium | 3:00 | review thw works and integrating the apis |  |  | Completed
|  |  |  | 18:00 | 19:00 |  | 1:00 | meet and countinue the lms work |  |  | Completed
2026-08-06 | 10:00 | 19:45 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | working on lms api integration and assist with kuberan |  |  | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | review the works and explain about flow of new onboarding flow for folleu to interns |  |  | Completed
|  |  |  | 18:00 | 19:45 | Medium | 1:45 | lms integration |  |  | Completed
0:00
2026-09-06 | 10:00 | 24:00 | task assign | 10:00 | 11:00 | Medium | 1:00 | review the works and assiging the task |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | lms api integration |  |  | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | lms api integration and review the works |  |  | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 18:30 | 24:00 | High | 5:30 | lms api integration |  |  | Completed
0:00
2026-10-06 | 0:00 | 13:00 | lms | 10:00 | 11:00 | Medium | 1:00 | lms integration |  |  | Completed
|  |  |  | 11:00 | 11:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | meet with aloha |  |  | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | lms api integration and review the works |  |  | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 18:30 | 24:00 | High | 5:30 | lms api integration |  |  | Completed
0:00
2026-11-06 | 0:00 | 13:00 | lms | 11:00 | 11:30 | Low | 0:30 | meet with aloha |  |  | Completed
|  |  |  | 11:30 | 14:00 | High | 2:30 | meet with aloha |  |  | Completed
|  |  |  | 15:00 | 18:00 | High | 3:00 | lms api integration and review the works |  |  | Completed
|  |  |  | 18:00 | 18:30 | Low | 0:30 | meet |  |  | Completed
|  |  |  | 18:30 | 24:00 | High | 5:30 | lms api integration |  |  | Completed
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00